## Sheet1
tab	recruitment	input	output	2nd input		Time
Upload	old file alreay uploaded for month year checking.	month,year	already upload is not???	append or replace	Frontend & backend
control pannel	mapping file delete then all mapping reset,achievement file delete then only reset these file	month,year, file type (mapper,achieve)			backend
File Upload Selector	month wise uploaded file details	month,year	uploaded file		backend
If filtered in mapped KPI and a particular parameter is edited then going back the same filter should appear					Frontend
Fos
COR Download tab need to given with employee select tab also					Frontend & backend
COR actual in incorrect					backend
Value disclaimer need (Cr/Lacs)					backend
Mapped data Download tab based on employee code , channel and Sub channel Vertical					Frontend & backend
Score Generation Failed						1. File related issues( Blank file, No data, Wrong Data, Missed upload) / 2. User is generating the score, when server is stopped	Need to add Validation from Upload file to Score Generation / track the users activity, Logs
Some Error Occurred						1. file upload is pending from User, Uploading blank file or wrong data(e.g. Target file employee codes are not present in mapper) / 2. RAM full	Need to add Validation and increase the Storage
Huge Time Taking for Manual Mapping						1. Mapping is happening sequentially with manual intervention	Need to remove manual intervention and mapping will happen sequentially in backend. if there is any error related to data it will appear in the status tab
Huge Time Taking for Uploading File						Upload becomes problematic when errors are highlighted. / Rectifying the errors need manual intervention	Database integration required / we will relook the Architecture for excel file uploading
Notification Time extend and Button provide							Need to remove manual intervention and mapping will happen sequentially in backend. if there is any error related to data it will appear in the status tab
File Upload Error should pop if format not match
Score generation pop-up which file is not uploaded						file upload is pending from User, Uploading blank file or wrong data(e.g. Target file employee codes are not present in mapper)
We have to upload all the files again if we find change in one file
Duplicate data uploaded need pop up for over write on previous data
Changed Data mapping run for score calculation